## README
NileCare – ISO/IEC 27001:2022 Annex A Gap Assessment
Scope | All 93 Annex A controls (2022 edition), assessed against the fictional company NileCare (private clinics, Cairo, ~120 staff).
Scoring | Implemented = 1, Partially implemented = 0.5, Not implemented = 0. Not applicable controls are excluded from the percentage.
Compliance % | Sum of scores divided by number of applicable controls. A simple maturity indicator, not a certification result.
Link to risks | The 'Related Risks' column points to Risk IDs in the NileCare Risk Register workbook.
Legend | Blue text = input (edit these). Black text = formulas.
Assumptions | All findings are invented for practice. Statuses were set to be consistent with the risk register (e.g. no MFA, untested backups, no SIEM). Controls 8.4 and 8.25 are not applicable because NileCare has no in-house development; the booking portal is built by an external agency.

## Gap Assessment
Control ID | Control | Theme | Status | Score (auto) | Current State | Gap / Recommended Action | Priority | Owner | Related Risks
5.1 | Policies for information security | Organizational | Partially implemented | 0.5 | Short IT usage policy exists; no approved ISMS policy set | Approve top-level information security policy and topic-specific policies; review yearly | High | IT Manager
5.2 | Information security roles and responsibilities | Organizational | Not implemented | 0 | Security duties not formally assigned | Define ISMS roles and owners in a RACI matrix | High | IT Manager
5.3 | Segregation of duties | Organizational | Partially implemented | 0.5 | Finance approvals are segregated; IT admins can request and approve access | Separate access request and approval | Medium | IT Manager
5.4 | Management responsibilities | Organizational | Partially implemented | 0.5 | Management supports IT but no security objectives set | Set security objectives; hold quarterly management review | Medium | IT Manager
5.5 | Contact with authorities | Organizational | Not implemented | 0 | No contact list for authorities | Keep contacts for EG-CERT, data protection authority and cyber police | Low | IT Manager
5.6 | Contact with special interest groups | Organizational | Not implemented | 0 | No participation in security communities | Join EG-CERT bulletins and healthcare security groups | Low | IT Manager
5.7 | Threat intelligence | Organizational | Not implemented | 0 | No threat intelligence used | Subscribe to EG-CERT and vendor advisories; review monthly | Medium | IT Manager
5.8 | Information security in project management | Organizational | Not implemented | 0 | Security not part of IT project steps | Add a security checklist to every IT project | Low | IT Manager
5.9 | Inventory of information and other associated assets | Organizational | Partially implemented | 0.5 | Asset inventory created in this project; no maintenance process yet | Assign owners and review the inventory twice a year | Medium | IT Manager
5.10 | Acceptable use of information and other associated assets | Organizational | Partially implemented | 0.5 | Acceptable use text in handbook; not signed by staff | Sign acceptable use policy at onboarding | Low | HR Manager
5.11 | Return of assets | Organizational | Partially implemented | 0.5 | Laptops collected on exit; tokens and accounts not always | Add return of assets to offboarding checklist | Low | HR Manager
5.12 | Classification of information | Organizational | Not implemented | 0 | No classification scheme | Adopt 4 levels: Public, Internal, Confidential, Patient-Restricted | Medium | Head of Medical Operations | R-12
5.13 | Labelling of information | Organizational | Not implemented | 0 | No labelling of documents or reports | Label documents by classification after 5.12 is approved | Low | IT Manager
5.14 | Information transfer | Organizational | Partially implemented | 0.5 | Patient reports sometimes sent by email; no secure transfer rules | Define secure transfer channels and encrypted email for patient data | Medium | IT Manager
5.15 | Access control | Organizational | Partially implemented | 0.5 | AD groups exist; no approved access control policy | Approve access control policy (see Access_Control_Policy.md) | High | IT Manager | R-02
5.16 | Identity management | Organizational | Partially implemented | 0.5 | Unique IDs for staff; shared accounts at some reception desks | Remove shared accounts; link IDs to HR records | High | IT Manager | R-02
5.17 | Authentication information | Organizational | Partially implemented | 0.5 | Password policy exists; MFA not enforced | Enforce MFA and password manager guidance | High | IT Manager
5.18 | Access rights | Organizational | Partially implemented | 0.5 | No periodic access review; leavers sometimes delayed | Quarterly access reviews; same-day removal for leavers | High | IT Manager | R-02
5.19 | Information security in supplier relationships | Organizational | Not implemented | 0 | No supplier security requirements or register | Create supplier register with risk tier and requirements | High | Procurement Manager | R-06
5.20 | Addressing information security within supplier agreements | Organizational | Not implemented | 0 | EMR vendor contract covers uptime only | Add security and breach-notification clauses to vendor contracts | High | Procurement Manager | R-06
5.21 | Managing information security in the ICT supply chain | Organizational | Not implemented | 0 | Hardware and software suppliers not assessed | Include supply chain requirements in procurement | Medium | Procurement Manager
5.22 | Monitoring, review and change management of supplier services | Organizational | Not implemented | 0 | No supplier reviews | Annual supplier security review for critical vendors | Medium | Procurement Manager
5.23 | Information security for use of cloud services | Organizational | Not implemented | 0 | EMR and email are cloud-based; no cloud policy or exit plan | Cloud usage policy with shared responsibility and exit plan | High | IT Manager | R-06
5.24 | Information security incident management planning and preparation | Organizational | Not implemented | 0 | No incident response plan | Approve incident response policy and playbooks (see Incident_Response_Policy.md) | High | IT Manager
5.25 | Assessment and decision on information security events | Organizational | Not implemented | 0 | No triage criteria | Define severity levels and escalation path | Medium | IT Manager
5.26 | Response to information security incidents | Organizational | Partially implemented | 0.5 | IT fixes issues ad hoc; no defined response steps | Use documented response phases and roles | High | IT Manager
5.27 | Learning from information security incidents | Organizational | Not implemented | 0 | No post-incident reviews | Hold a review after each major incident and track actions | Medium | IT Manager
5.28 | Collection of evidence | Organizational | Not implemented | 0 | No evidence handling procedure | Define log and disk evidence preservation steps | Low | IT Manager
5.29 | Information security during disruption | Organizational | Not implemented | 0 | Security controls not planned for outages | Define minimum security controls during disruption | Medium | IT Manager
5.30 | ICT readiness for business continuity | Organizational | Partially implemented | 0.5 | Backups exist; no tested DR or continuity plan | Create DR plan with recovery targets; test yearly | High | IT Manager | R-04, R-08
5.31 | Legal, statutory, regulatory and contractual requirements | Organizational | Partially implemented | 0.5 | Aware of Egypt PDPL (Law 151 of 2020); no requirements register | Maintain legal requirements register; appoint DPO | High | Legal and Compliance | R-14
5.32 | Intellectual property rights | Organizational | Partially implemented | 0.5 | Clinical systems licensed; workstation software not fully tracked | Software license inventory and audit | Low | IT Manager
5.33 | Protection of records | Organizational | Partially implemented | 0.5 | Medical records follow clinical retention rules; other records have none | Retention schedule for all record types | Medium | Legal and Compliance
5.34 | Privacy and protection of PII | Organizational | Not implemented | 0 | No privacy notice, consent process or breach procedure | Privacy notice, consent forms, data subject request and breach process | High | Legal and Compliance | R-14
5.35 | Independent review of information security | Organizational | Not implemented | 0 | No internal or external audit | Annual internal audit against ISO 27001 | Medium | IT Manager
5.36 | Compliance with policies, rules and standards for information security | Organizational | Not implemented | 0 | No compliance checks | Quarterly compliance spot-checks | Medium | IT Manager
5.37 | Documented operating procedures | Organizational | Partially implemented | 0.5 | Some runbooks held by individuals | Centralize and version operating procedures | Medium | IT Manager | R-16
6.1 | Screening | People | Implemented | 1 | Background and license checks for doctors and nurses; HR checks for all hires | - | - | HR Manager
6.2 | Terms and conditions of employment | People | Partially implemented | 0.5 | Contracts include confidentiality; no security responsibilities clause | Add information security responsibilities to contracts | Low | HR Manager
6.3 | Information security awareness, education and training | People | Not implemented | 0 | No security awareness program | Annual training plus quarterly phishing simulations | High | HR Manager | R-03
6.4 | Disciplinary process | People | Partially implemented | 0.5 | General disciplinary process; not linked to security breaches | Link policy violations to disciplinary process | Low | HR Manager
6.5 | Responsibilities after termination or change of employment | People | Partially implemented | 0.5 | No checklist; access revocation varies | Offboarding checklist with access revocation SLA | Medium | HR Manager | R-16
6.6 | Confidentiality or non-disclosure agreements | People | Implemented | 1 | NDAs signed by all employees | - | - | HR Manager
6.7 | Remote working | People | Not implemented | 0 | Doctors access EMR remotely; no remote work rules | Remote work policy with VPN and MFA requirement | Medium | HR Manager
6.8 | Information security event reporting | People | Partially implemented | 0.5 | Staff tell IT informally | Single reporting channel (email and phone) with awareness | Medium | HR Manager
7.1 | Physical security perimeters | Physical | Implemented | 1 | Reception desks and locked doors at all branches | - | - | Facilities Manager
7.2 | Physical entry | Physical | Partially implemented | 0.5 | Badge readers at HQ only; branch visitors logged on paper | Extend badge or visitor log to all branches | Medium | Facilities Manager
7.3 | Securing offices, rooms and facilities | Physical | Partially implemented | 0.5 | Server room locked; keys held by several people | Restrict and log server room access | Medium | Facilities Manager
7.4 | Physical security monitoring | Physical | Implemented | 1 | CCTV covers entrances and server room at all branches | - | - | Facilities Manager
7.5 | Protecting against physical and environmental threats | Physical | Partially implemented | 0.5 | Fire extinguisher only; no environmental monitoring | Temperature and water sensors; fire suppression review | Medium | Facilities Manager | R-08
7.6 | Working in secure areas | Physical | Partially implemented | 0.5 | Medical areas controlled; rules not documented | Document rules for secure areas | Low | Facilities Manager
7.7 | Clear desk and clear screen | Physical | Not implemented | 0 | No clear desk or auto-lock rule | Auto-lock screens at 5 minutes; clear desk rule | Medium | Facilities Manager
7.8 | Equipment siting and protection | Physical | Partially implemented | 0.5 | Server rack protected; branch network cabinets unlocked | Lock branch network cabinets | Medium | Facilities Manager
7.9 | Security of assets off-premises | Physical | Partially implemented | 0.5 | Laptops used outside clinics without rules | Rules for off-site equipment; encryption | Medium | IT Support Lead
7.10 | Storage media | Physical | Not implemented | 0 | No removable media rules | Block USB storage by default; approved media only | Low | Facilities Manager
7.11 | Supporting utilities | Physical | Partially implemented | 0.5 | UPS covers servers; no generator | Add second UPS; assess generator for HQ | Medium | Facilities Manager | R-08
7.12 | Cabling security | Physical | Partially implemented | 0.5 | Structured cabling at HQ; branches unlabelled | Label and protect cabling at branches | Low | Facilities Manager
7.13 | Equipment maintenance | Physical | Implemented | 1 | Vendor maintenance contracts for servers and medical devices | - | - | Facilities Manager
7.14 | Secure disposal or re-use of equipment | Physical | Partially implemented | 0.5 | Old PCs reused without verified wiping | Certified wipe and disposal log | Medium | IT Support Lead
8.1 | User endpoint devices | Technological | Not implemented | 0 | Laptops not encrypted; no device management | Full-disk encryption and device management with remote wipe | High | IT Support Lead | R-07
8.2 | Privileged access rights | Technological | Not implemented | 0 | Admin accounts used for daily work | Separate admin accounts; privileged access management | High | IT Manager | R-09
8.3 | Information access restriction | Technological | Partially implemented | 0.5 | EMR roles exist; file server shares are broad | Review shares; least-privilege groups | Medium | IT Manager | R-02
8.4 | Access to source code | Technological | Not applicable |  | No in-house source code; portal built by external agency (see 8.30) | - | - | IT Manager
8.5 | Secure authentication | Technological | Partially implemented | 0.5 | Password policy only; no MFA on email, VPN or admin accounts | Enforce MFA on email, VPN and admin accounts | High | IT Manager | R-03, R-09
8.6 | Capacity management | Technological | Partially implemented | 0.5 | No capacity monitoring on servers | Basic disk and CPU monitoring with thresholds | Low | IT Manager
8.7 | Protection against malware | Technological | Partially implemented | 0.5 | Antivirus on workstations; no EDR on servers | Deploy EDR on servers and laptops | High | IT Manager | R-01
8.8 | Management of technical vulnerabilities | Technological | Not implemented | 0 | No regular scans; patching is manual and delayed | Monthly patch cycle; quarterly vulnerability scans | High | IT Manager | R-01, R-05, R-15
8.9 | Configuration management | Technological | Not implemented | 0 | No baseline configurations | Baselines for servers, firewalls and switches | Medium | IT Manager
8.10 | Information deletion | Technological | Not implemented | 0 | No deletion rules | Deletion procedure following retention schedule | Low | IT Manager
8.11 | Data masking | Technological | Not implemented | 0 | Patient identifiers shown in full in reports | Mask identifiers in reports and test data | Low | IT Manager
8.12 | Data leakage prevention | Technological | Not implemented | 0 | No DLP; data can leave via email and personal cloud | DLP rules for patient identifiers on email | Medium | IT Manager | R-12
8.13 | Information backup | Technological | Partially implemented | 0.5 | Nightly backups; restore never tested; NAS on production network | Offline or immutable copy; quarterly restore tests | High | IT Manager | R-04
8.14 | Redundancy of information processing facilities | Technological | Partially implemented | 0.5 | Single PACS storage node; no failover | Failover for critical systems based on recovery targets | Medium | IT Manager | R-08, R-13
8.15 | Logging | Technological | Partially implemented | 0.5 | Logs kept on devices; not centralized or protected | Centralize logs for servers, AD, firewalls and EMR access | High | IT Manager | R-02
8.16 | Monitoring activities | Technological | Not implemented | 0 | No monitoring or alerting | Deploy SIEM and define priority alerts (failed logins, admin changes, EMR bulk access) | High | IT Manager | R-01
8.17 | Clock synchronization | Technological | Implemented | 1 | All servers and devices sync to AD time service | - | - | IT Manager
8.18 | Use of privileged utility programs | Technological | Not implemented | 0 | No restriction on admin tools | Restrict admin tools to admin accounts and log use | Low | IT Manager
8.19 | Installation of software on operational systems | Technological | Partially implemented | 0.5 | Users can install software on workstations | Remove local admin rights; approved software list | Medium | IT Support Lead | R-15
8.20 | Networks security | Technological | Partially implemented | 0.5 | Firewalls at each site; flat internal network | Segment network; review firewall rules | High | Network Administrator | R-10
8.21 | Security of network services | Technological | Partially implemented | 0.5 | ISP and VPN SLAs cover uptime only | Add security requirements to network service contracts | Medium | Network Administrator
8.22 | Segregation of networks | Technological | Not implemented | 0 | No VLANs for clinical, admin, POS or guest | Create VLANs and inter-VLAN firewall rules | High | Network Administrator | R-01, R-11
8.23 | Web filtering | Technological | Not implemented | 0 | No web filtering | Category-based web filtering on firewall or proxy | Medium | Network Administrator
8.24 | Use of cryptography | Technological | Partially implemented | 0.5 | HTTPS on portal; laptops unencrypted; old VPN keys | Cryptography policy; encrypt laptops; rotate VPN keys | High | IT Manager | R-07, R-10
8.25 | Secure development life cycle | Technological | Not applicable |  | No in-house development (external agency builds the portal) | - | - | IT Manager
8.26 | Application security requirements | Technological | Not implemented | 0 | No security requirements for portal | Define portal security requirements in agency contract | Medium | Digital Services Lead
8.27 | Secure system architecture and engineering principles | Technological | Not implemented | 0 | No architecture principles | Document basic architecture principles | Low | IT Manager
8.28 | Secure coding | Technological | Not implemented | 0 | No secure coding requirement for agency | Require OWASP-based secure coding from agency | Medium | Digital Services Lead | R-05
8.29 | Security testing in development and acceptance | Technological | Not implemented | 0 | No security test before release | Security test before each portal release | Medium | Digital Services Lead
8.30 | Outsourced development | Technological | Partially implemented | 0.5 | Agency contract exists; no security clauses | Add security clauses and code review rights | Medium | Digital Services Lead
8.31 | Separation of development, test and production environments | Technological | Partially implemented | 0.5 | Agency uses separate staging; not verified | Verify separation during supplier review | Low | Digital Services Lead
8.32 | Change management | Technological | Partially implemented | 0.5 | Changes approved verbally; no change log | Change log with approval and rollback plan | Medium | IT Manager
8.33 | Test information | Technological | Not implemented | 0 | Real patient data may be used for testing | Use masked data for tests | Low | IT Manager
8.34 | Protection of information systems during audit testing | Technological | Not implemented | 0 | No rules for audit or pentest access | Define scope, timing and approval for testing | Low | IT Manager

## Summary
Theme | Total Controls | Applicable | Implemented | Partially Implemented | Not Implemented | Not Applicable | Compliance %
Organizational | 37 | 37 | 0 | 17 | 20 | 0 | 22.97%
People | 8 | 8 | 2 | 4 | 2 | 0 | 50%
Physical | 14 | 14 | 3 | 9 | 2 | 0 | 53.57%
Technological | 34 | 32 | 1 | 14 | 17 | 2 | 25%
Total | 93 | 91 | 6 | 44 | 41 | 2 | 30.77%
Open gaps by priority | Count
High | 26
Medium | 38
Low | 21
Total open gaps | 85
Note | Compliance % = (Implemented x 1 + Partially x 0.5) / Applicable controls. Priority applies to open gaps only.