## README
NileCare – ISO/IEC 27001:2022 Risk Assessment (Practice Project)
Company (fictional) | NileCare – private clinics group in Cairo, 3 branches, ~120 staff, electronic patient records (EMR) and an online booking portal.
Purpose | Portfolio GRC project: asset inventory, risk register, and treatment plan mapped to ISO 27001:2022 Annex A.
Method | Risk = Likelihood (1-5) x Impact (1-5). Impact is driven by the asset's Confidentiality/Integrity/Availability ratings. See 'Scoring Key'.
Sheets
Asset Inventory | 20 assets with owner, location, C/I/A ratings (1-3) and auto-calculated criticality.
Risk Register | 16 risks linked to assets by Asset ID. Inherent and residual scores and levels are formulas.
Scoring Key | Likelihood and impact scales, risk-level thresholds (the thresholds are read by the formulas).
Summary | Auto-counts of risks by level, before and after treatment.
Legend
Blue text | Input cells – edit these (ratings, owners, text).
Black text | Formulas – do not overwrite.
Assumptions | All assets, risks, owners and ratings are fictional and invented for practice. Annex A references follow the 2022 edition numbering. Egyptian Personal Data Protection Law No. 151 of 2020 is referenced for PII-related risks.

## Asset Inventory
Asset ID | Asset Name | Type | Description | Location | Owner | Confidentiality (1-3) | Integrity (1-3) | Availability (1-3) | Criticality (auto)
A-01 | EMR System (patient records) | Application | Electronic medical records used by all clinics | Cloud (Egyptian hosting provider) | Head of Medical Operations | 3 | 3 | 3 | High
A-02 | Patient Database | Data | Patient identity, history, diagnoses, prescriptions | Primary DB server | IT Manager | 3 | 3 | 3 | High
A-03 | Online Booking Portal | Application | Public website for appointment booking | Cloud web hosting | Digital Services Lead | 2 | 2 | 3 | High
A-04 | Core DB Server | Hardware | On-prem server hosting EMR database replica | HQ server room, Cairo | IT Manager | 3 | 3 | 3 | High
A-05 | File Server | Hardware | Shared drives for admin and finance documents | HQ server room, Cairo | IT Manager | 2 | 2 | 2 | Medium
A-06 | Backup System (NAS + cloud copy) | Hardware | Nightly backups of EMR and file server | HQ server room + cloud | IT Manager | 3 | 3 | 2 | High
A-07 | Core Network (firewalls, switches) | Network | Firewalls, core and branch switches | HQ and 3 branches | Network Administrator | 2 | 3 | 3 | High
A-08 | Branch VPN Links | Network | Site-to-site VPN between branches and HQ | All branches | Network Administrator | 3 | 3 | 3 | High
A-09 | Staff Workstations (~80) | Hardware | Reception and admin PCs | All branches | IT Support Lead | 2 | 2 | 2 | Medium
A-10 | Doctor Laptops (~35) | Hardware | Laptops used for consultations and EMR access | Clinics | IT Support Lead | 3 | 3 | 2 | High
A-11 | Email and Collaboration (SaaS) | Service | Corporate email and file sharing | Cloud SaaS | IT Manager | 3 | 2 | 2 | High
A-12 | Active Directory | Service | Staff identities, groups and authentication | HQ server room | IT Manager | 3 | 3 | 3 | High
A-13 | Lab Information System | Application | Lab orders and results (integrated with EMR) | Cloud (vendor-hosted) | Head of Laboratory | 3 | 3 | 3 | High
A-14 | Medical Imaging (PACS) | Application | X-ray and ultrasound image storage | Branch 1 and HQ | Head of Radiology | 3 | 3 | 2 | High
A-15 | Payment POS and Billing System | Application | Card payments and invoicing | All branches | Finance Manager | 3 | 3 | 2 | High
A-16 | CCTV and Door Access System | Hardware | Cameras and badge readers | All branches | Facilities Manager | 1 | 2 | 2 | Medium
A-17 | HR Records | Data | Employee contracts, payroll, personal data | HR cabinet and HR system | HR Manager | 3 | 2 | 1 | High
A-18 | Clinical Staff (doctors, nurses) | People | Users with privileged access to patient data | All branches | Head of Medical Operations | 3 | 3 | 3 | High
A-19 | IT Team (5 staff) | People | Administrators of all systems | HQ | IT Manager | 3 | 3 | 3 | High
A-20 | Third-party IT and EMR Vendor | Supplier | Vendor providing EMR hosting and support | External | Procurement Manager | 3 | 3 | 3 | High

## Risk Register
Risk ID | Asset ID | Asset Name (auto) | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Level | Existing Controls | ISO 27001:2022 Annex A Control | Treatment | Planned Actions | Risk Owner | Target Date | Residual Likelihood | Residual Impact | Residual Score | Residual Level | Status
R-01 | A-01 | EMR System (patient records) | Ransomware encrypts EMR and databases | Flat network, delayed patching, limited EDR coverage | 4 | 5 | 20 | Critical | Daily backups; basic antivirus | A.8.7 Protection against malware; A.8.8 Technical vulnerabilities | Mitigate | Deploy EDR on servers and laptops; network segmentation; monthly patch cycle | IT Manager | 2027-03-31 | 2 | 4 | 8 | Medium | Planned
R-02 | A-02 | Patient Database | Unauthorized access to patient records by staff (snooping) | No role-based access review; shared accounts at some reception desks | 4 | 4 | 16 | High | Basic AD groups | A.5.15 Access control; A.8.15 Logging | Mitigate | RBAC redesign; disable shared accounts; log and review EMR access | Head of Medical Operations | 2027-02-28 | 2 | 3 | 6 | Medium | Planned
R-03 | A-03 | Online Booking Portal | Phishing leads to credential theft | Low security awareness; MFA not enforced on email | 5 | 4 | 20 | Critical | Spam filter | A.6.3 Awareness and training; A.8.5 Secure authentication | Mitigate | Enforce MFA on email and VPN; quarterly phishing simulations | IT Manager | 2027-01-31 | 3 | 3 | 9 | Medium | In progress
R-04 | A-06 | Backup System (NAS + cloud copy) | Backups corrupted or unrecoverable during an incident | Restore never tested; backup NAS on same network as production | 3 | 5 | 15 | High | Nightly backups | A.8.13 Information backup; A.5.30 ICT readiness for continuity | Mitigate | Offline/immutable copy; quarterly restore tests | IT Manager | 2027-02-15 | 2 | 3 | 6 | Medium | Planned
R-05 | A-03 | Online Booking Portal | Web attack (SQL injection, defacement) on booking portal | No WAF; no regular vulnerability scans | 3 | 3 | 9 | Medium | HTTPS only | A.8.8 Technical vulnerabilities; A.8.28 Secure coding | Mitigate | Deploy WAF; quarterly vulnerability scan and annual pentest | Digital Services Lead | 2027-04-30 | 2 | 2 | 4 | Low | Planned
R-06 | A-20 | Third-party IT and EMR Vendor | EMR vendor breach or outage affects patient data and availability | No security clauses or SLA audit rights in contract | 3 | 5 | 15 | High | Signed contract with SLA for uptime only | A.5.19 Supplier relationships; A.5.20 Supplier agreements; A.5.23 Cloud services | Mitigate | Add security and breach-notification clauses; annual vendor assessment | Procurement Manager | 2027-06-30 | 2 | 4 | 8 | Medium | Planned
R-07 | A-10 | Doctor Laptops (~35) | Loss or theft of doctor laptops with patient data | Laptops not encrypted | 3 | 4 | 12 | High | Asset tagging | A.8.1 User endpoint devices; A.8.24 Use of cryptography | Mitigate | Enable full-disk encryption (BitLocker) and remote wipe | IT Support Lead | 2027-01-15 | 1 | 3 | 3 | Low | In progress
R-08 | A-04 | Core DB Server | Server room outage (power, cooling, fire) | Single UPS; no environmental monitoring | 2 | 5 | 10 | High | UPS; fire extinguisher | A.7.5 Protecting against physical threats; A.8.14 Redundancy | Mitigate | Environmental sensors; second UPS; DR plan | Facilities Manager | 2027-05-31 | 2 | 3 | 6 | Medium | Planned
R-09 | A-12 | Active Directory | Privileged account compromise in Active Directory | No PAM; admin accounts used for daily work | 3 | 5 | 15 | High | Password policy | A.8.2 Privileged access rights; A.8.5 Secure authentication | Mitigate | Separate admin accounts; MFA; tiered admin model | IT Manager | 2027-03-15 | 2 | 4 | 8 | Medium | Planned
R-10 | A-08 | Branch VPN Links | Interception or misuse of branch VPN traffic | Old VPN configuration; weak pre-shared keys | 2 | 4 | 8 | Medium | IPsec VPN | A.8.20 Networks security; A.8.24 Use of cryptography | Mitigate | Rotate keys; move to certificate-based VPN; review configs | Network Administrator | 2027-02-28 | 1 | 3 | 3 | Low | Planned
R-11 | A-15 | Payment POS and Billing System | Payment card data theft from POS | POS terminals on same VLAN as workstations | 2 | 4 | 8 | Medium | Provider-managed terminals | A.8.22 Segregation of networks; A.5.34 Privacy and protection of PII | Mitigate | Dedicated POS VLAN; follow PCI DSS guidance | Finance Manager | 2027-03-31 | 1 | 3 | 3 | Low | Planned
R-12 | A-11 | Email and Collaboration (SaaS) | Sensitive data leaked via email or personal cloud sharing | No DLP; no data classification | 4 | 3 | 12 | High | Acceptable use policy | A.5.12 Classification of information; A.8.12 Data leakage prevention | Mitigate | Data classification scheme; DLP rules for patient IDs | IT Manager | 2027-04-30 | 2 | 2 | 4 | Low | Planned
R-13 | A-14 | Medical Imaging (PACS) | Medical images unavailable during PACS failure | Single storage node; no failover | 3 | 3 | 9 | Medium | Vendor support contract | A.8.14 Redundancy of information processing facilities | Accept | Accepted until budget cycle; images also kept on modalities for 14 days | Head of Radiology | 2027-06-30 | 3 | 2 | 6 | Medium | Accepted
R-14 | A-02 | Patient Database | Non-compliance with Egypt PDPL (Law 151/2020) leading to fines | No privacy notice, retention policy or breach process | 4 | 4 | 16 | High | None | A.5.34 Privacy and protection of PII; A.5.31 Legal requirements | Mitigate | Appoint DPO; privacy notice; retention schedule; breach-notification procedure | Legal and Compliance | 2027-03-31 | 2 | 3 | 6 | Medium | Planned
R-15 | A-09 | Staff Workstations (~80) | Unpatched or unlicensed software on workstations | No central patch management or asset-software inventory | 4 | 3 | 12 | High | Windows Update (manual) | A.8.8 Technical vulnerabilities; A.8.19 Installation of software | Mitigate | Deploy WSUS/Intune patching; software inventory | IT Support Lead | 2027-02-15 | 2 | 2 | 4 | Low | In progress
R-16 | A-19 | IT Team (5 staff) | Key IT admin leaves, causing knowledge loss and access gaps | No documentation; no offboarding checklist | 3 | 4 | 12 | High | None | A.6.5 Responsibilities after termination; A.5.37 Documented operating procedures | Mitigate | Runbooks; offboarding checklist; access revocation SLA | IT Manager | 2027-01-31 | 2 | 2 | 4 | Low | Planned

## Scoring Key
Level | Likelihood (1-5) | Impact (1-5)
1 | Rare – unlikely in 3+ years | Negligible – no real effect on patients or operations
2 | Unlikely – once every 1-3 years | Minor – small disruption, no data exposed
3 | Possible – once a year | Moderate – clinic disruption for a day, limited data exposure
4 | Likely – several times a year | Major – multi-day outage or exposure of patient records
5 | Almost certain – monthly or more | Severe – patient safety risk, mass data breach, legal action
Risk level thresholds (score = L x I) | Min score | Level
| 1 | Low
| 5 | Medium
| 10 | High
| 17 | Critical
Asset C/I/A rating | Meaning
1 | Low – little harm if compromised
2 | Medium – noticeable harm
3 | High – serious harm (patient safety, legal, financial)
Asset criticality (formula) | Highest of C, I, A: 1 = Low, 2 = Medium, 3 = High

## Summary
Risk Level | Inherent (before treatment) | Residual (after planned treatment)
Critical | 2 | 0
High | 10 | 0
Medium | 4 | 9
Low | 0 | 7
Total | 16 | 16
Average score | 13.0625 | 5.5
Risk reduction |  | 57.89%